## Sheet1
Project Name | Easy-A Learning
Project Manager | Michael Brown
Start Date | 2020-05-01 |  | End Date | 2020-12-20
Project Deliverable | Estimated time
Hiring Applacation Development Team | 1 week/40 hrs
Sketching/Wireframing | 2 weeks/80 hrs
Design Style Guide | 1 month
Development Quality Assurance & Feedback | 6 months/40 hrs per week
Positions/Roles | Estimated time | Cost
Jr. UI Designer | 7 hours per day | $75/hr
Sr. UI Designer | 7 hours per day | $90/hr
Jr. Front-End Developer | 7 hours per day | $75/hr
Sr. Front-End Developer | 7 hours per day | $90/hr
Jr. Back-End Developer | 7 hours per day | $80/hr
Sr. Back-End Developer | 7 hours per day | $90/hr
Lead Developer | 7 hours per day | $120/hr
Jr. QA Tester | 7 hours per day | $75/hr
Sr. QA Tester | 7 hours per day | $78/hr
Project Manager | 7 hours per day | $150/hr